## WPI HIGH LEVEL PLAN
Key Activities | 2026 | [11 empty] | 2027
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A
CC22 LHD MEX | 2026 J: IM; 2026 A: CM; 2026 J: SFM; 2026 J: SHRM; 2026 N: X1; 2026 D: X2; 2027 F: LRM; 2027 M: PBM; 2027 A: BM
| WK03 |  |  | WK17 |  | WK23 | WK30 |  |  |  | WK45 | WK52 |  | WK08 | WK13 | WK16
[14 empty] | X3 |  | SOPM
[14 empty] | WK09 |  | WK18
CC22 LHD MEA | 2026 J: IM; 2026 A: CM; 2026 J: SFM; 2026 O: SHRM; 2027 F: X1; 2027 M: X2; 2027 M: LRM; 2027 J: PBM; 2027 J: BM
| WK03 |  |  | WK15 |  | WK23 |  |  |  | WK40 |  |  |  | WK07 | WK12 |  | WK19 | WK26 | WK29
[17 empty] | X3 |  | SOPM
[17 empty] | WK20 |  | WK31
WPI LOOP MAPPING | 2026 J: Digital Phase; 2026 O: Physical Phase
| LOOP -2 |  |  |  | LOOP -1 |  | LOOP 0 |  |  |  | LOOP 1, 2, 3, 4 |  |  |  | LOOP 5
§Discussion with Global LMO and understand WPI requirement & Methodology | bar: 2026 M to 2026 M
§Preparation of WPI customized Kick off material | bar: 2026 M to 2026 J
§Kick off meeting with plant and project team | bar: 2026 J
§Prepare Loop wise check list based on Project applicability | bar: 2026 M to 2026 J
§Hot housing with CFT (front loading approach) | bar: 2026 A to 2026 O
§WPI station virtual mapping preparation | bar: 2026 J to 2026 N
§WPI virtual & physical connect with RJN PWT plant to understand the virtual board preparation & Gemba approach | bar: 2026 J to 2026 J
§Team leader training & Gemba assessment with CFT ( O&R / SQAM approach ) | bar: 2026 J to 2027 J
§Daily connect with working level | bar: 2026 A to 2027 J
§Weekly connect with leadership | bar: 2026 O to 2027 J
Current Status  LOOP-0 :
23%(10/44) stations assessment completed, Remaining 34 station assessment completion by WK49’26
41%(100/242) observations closed. Remaining 142 issues CFT convergence inprogress thru daily meeting

## WPI IMPLEMENTATION DETAIL PLAN (hidden)
WPI Station Wise Assessment Timing Plan
Assessment Standard Creteria | Activity Details | Plan Vs Actual | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | Sep'26 | [29 empty] | Oct'26 | [30 empty] | Nov'26 | [29 empty] | 2026-12-01
|  |  | WK27 |  |  |  |  | WK28 | [6 empty] | WK29 | [6 empty] | WK30 | [6 empty] | WK31 | [6 empty] | WK32 | [6 empty] | WK33 | [6 empty] | WK34 | [6 empty] | WK35 | [6 empty] | WK36 | [6 empty] | WK37 | [6 empty] | WK38 | [6 empty] | WK39 | [6 empty] | WK40 | [6 empty] | WK41 | [6 empty] | WK42 | [6 empty] | WK43 | [6 empty] | WK44 | [6 empty] | WK45 | [6 empty] | WK46 | [6 empty] | WK47 | [6 empty] | WK48 | [6 empty] | WK49 | [6 empty] | WK50 | [6 empty] | WK51 | [6 empty] | WK52 | [6 empty] | WK01
No of stations | time axis 2026-07-01 to 2026-12-31
 | time axis 2026-07-01 to 2026-12-31
Safety | JSRA | Plan | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
|  | Actual | 2026-08-31: C10; 2026-09-03: PBS; 2026-09-07: T10RH; 2026-09-09: T10LH; 2026-09-14: T20E; 2026-09-17: T20LH; 2026-09-21: T20RH; 2026-09-24: T30E; 2026-09-28: T30LH; 2026-10-01: T30RH; 2026-10-05: T40RH; 2026-10-08: T50RH; 2026-10-12: T50LH | 13
| MURI Analysis | Plan | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
|  | Actual | 2026-07-20: C10; 2026-07-22: T10RH; 2026-07-24: T10LH; 2026-07-27: T20RH; 2026-07-29: T20LH; 2026-07-31: T20E; 2026-08-03: T30RH; 2026-08-05: T30LH; 2026-08-07: T30E; 2026-08-10: T40RH; 2026-08-12: T50RH; 2026-08-14: T50LH; 2026-08-17: T50E; 2026-08-19: T60E; 2026-08-21: T70RH; 2026-08-24: T70LH; 2026-08-26: T90RH; 2026-08-28: T90LH; 2026-08-31: C40RH; 2026-09-02: P10RH; 2026-09-04: P20LH; 2026-09-07: P30RH; 2026-09-09: P30LH; 2026-09-11: C45RR; 2026-09-14: C70; 2026-09-16: C80RH; 2026-09-18: F10RH; 2026-09-21: F10LH; 2026-09-23: F10E; 2026-09-25: F20RH; 2026-09-28: F20LH; 2026-09-30: F30RH; 2026-10-02: F30LH; 2026-10-05: F40RH; 2026-10-07: F40LH; 2026-10-09: F60RH; 2026-10-12: F60LH; 2026-10-14: F70RH; 2026-10-16: F70LH; 2026-10-19: F80RH; 2026-10-21: F80LH; 2026-10-23: F90RH; 2026-10-26: F90LH | 43
Customer Experience | O&R Study | Plan | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
|  | Actual | 2026-09-16: C10; 2026-09-18: PBS; 2026-09-21: T10LH; 2026-09-23: T10RH; 2026-09-25: T20E; 2026-09-28: T20LH; 2026-09-30: T20RH; 2026-10-01: T30E; 2026-10-02: T30LH; 2026-10-05: T30RH; 2026-10-07: T40RH; 2026-10-12: T50RH; 2026-10-14: T50LH | 13
| LLR / Mountability Confirmation & Validation | [185 empty] | 0
Logistics | Material classification study |  | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
| Flow analysis |  | 2026-07-20: C10; 2026-07-21: T10RH; 2026-07-22: T10LH; 2026-07-23: T20RH; 2026-07-24: T20LH; 2026-07-25: T20E; 2026-07-27: T30RH; 2026-07-28: T30LH; 2026-07-29: T30E; 2026-07-30: T40RH; 2026-07-31: T50RH; 2026-08-03: T50LH; 2026-08-04: T50E; 2026-08-05: T60E; 2026-08-06: T70RH; 2026-08-07: T70LH; 2026-08-08: T90RH; 2026-08-10: T90LH; 2026-08-11: C40RH; 2026-08-12: P10RH; 2026-08-13: P20LH; 2026-08-14: T30RH; 2026-08-17: P30LH; 2026-08-18: C45RR; 2026-08-19: R20; 2026-08-20: C70; 2026-08-21: C80RH; 2026-08-22: F10RH; 2026-08-24: F10LH; 2026-08-25: F10E; 2026-08-26: F20RH; 2026-08-27: F20LH; 2026-08-28: F30RH; 2026-08-31: F30LH; 2026-09-01: F40RH; 2026-09-02: F40LH; 2026-09-03: F60RH; 2026-09-04: F60LH; 2026-09-05: F70RH; 2026-09-07: F70RH; 2026-09-08: F80RH; 2026-09-09: F80LH; 2026-09-10: F90RH; 2026-09-11: F90LH | 44
| Workstation Area calculation | [185 empty] | 0
| Parts stock management | [185 empty] | 0
Workplace organization | Process sequence analysis | Plan | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
| Model matrix mapping | [185 empty] | 0
| VA & NVA Study | Actual | 2026-09-07: C10; 2026-09-09: PBS; 2026-09-14: T10LH; 2026-09-16: T10RH; 2026-09-18: T20E; 2026-09-21: T20LH; 2026-09-23: T20RH; 2026-09-28: T30E; 2026-10-01: T30LH; 2026-10-05: T30RH; 2026-10-07: T40RH; 2026-10-12: T50RH; 2026-10-14: T50LH | 13
| Spaghetti study | [185 empty] | 0
Workstation grid | Global workstation assessment grid | Plan | 2026-07-20: C10; 2026-07-23: PBS; 2026-07-27: T10RH; 2026-07-29: T10LH; 2026-08-06: T20RH; 2026-08-10: T20LH; 2026-08-13: T20E; 2026-08-17: T20E; 2026-08-18: T30RH; 2026-08-21: T30LH; 2026-08-24: T30E; 2026-08-27: T40RH; 2026-08-31: T50RH; 2026-09-03: T50LH; 2026-09-07: T50E; 2026-09-09: T60E; 2026-09-14: T70RH; 2026-09-17: T70LH; 2026-09-21: T90RH; 2026-09-24: T90LH; 2026-09-28: C40RH; 2026-09-30: P10RH; 2026-10-05: P20LH; 2026-10-08: P30RH; 2026-10-12: P30LH; 2026-10-14: C45RR; 2026-10-19: C70; 2026-10-22: C80RH; 2026-10-26: F10RH; 2026-10-28: F10LH; 2026-11-02: F10E; 2026-11-05: F20LH; 2026-11-09: F20RH; 2026-11-11: F30RH; 2026-11-16: F30LH; 2026-11-19: F40RH; 2026-11-23: F40LH; 2026-11-25: F60RH; 2026-12-02: F70RH; 2026-12-04: F70LH; 2026-12-07: F80RH; 2026-12-10: F80LH; 2026-12-14: F90RH; 2026-12-17: F90LH | 44
|  | Actual | 2026-09-07: C10; 2026-09-09: PBS; 2026-09-14: T10LH; 2026-09-17: T10RH; 2026-09-21: T20E; 2026-09-24: T20LH; 2026-09-28: T20RH; 2026-09-30: T30E; 2026-10-05: T30LH; 2026-10-08: T30RH; 2026-10-12: T40RH; 2026-10-14: T50RH | 12
| Papper Scroll Mapping |  | 2026-07-30: Station wise overall papper scroll mapping & actions convergence | 1
| O&R ( Lite PFMEA ) |  | 2026-08-04: Detailed station process wise O&R study with QCP | 1
| Proactive SQAM Assessment |  | 2026-08-07: Process wise SQAM assessment | 1
| Line Balancing Workshop ( VA & NVA assessment ) |  | 2026-07-23: Station wise Value Added & Non-Value added study & NVA Reduction opportunity identification | 1
| JES creation ( Digi JES with Conversion of Local language ) | [185 empty] | 0 | bar: 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04; 2026-09-07 to 2026-09-11; 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02; 2026-10-05 to 2026-10-09; 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30
| Workstation Grid Validation | [185 empty] | 0 | bar: 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04; 2026-09-07 to 2026-09-11; 2026-09-14 to 2026-09-18; 2026-09-21 to 2026-09-25; 2026-09-28 to 2026-10-02; 2026-10-05 to 2026-10-09; 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-12
| Daily CFT Gemba Meeting ( 4:30 : 5:30 PM ) |  | 2026-07-20: *Daily Gemba connect with CFT - WPI Progress review | 1
0 | bar: 2026-07-01 to 2026-07-03; 2026-07-06 to 2026-07-10; 2026-07-13 to 2026-07-17; 2026-07-20 to 2026-07-24; 2026-07-27 to 2026-07-31; 2026-08-03 to 2026-08-07; 2026-08-10 to 2026-08-14; 2026-08-17 to 2026-08-21; 2026-08-24 to 2026-08-28; 2026-08-31 to 2026-09-04
| Station - 1 : Pilot Station ( C10 ) | P | 2026-07-13: LL Validation; 2026-07-15: Station Layout Validation; 2026-07-22: JSRA / Ergo assessment; 2026-07-29: VA / NVA study; 2026-08-03: O&R and Logistics assessment | 5
A | bar: 2026-07-13 to 2026-07-17; 2026-07-20 to 2026-07-24; 2026-07-27 to 2026-08-01; 2026-08-03 to 2026-08-05
| Station - 2 : PBS | P | [184 empty] | 0 | bar: 2026-08-03 to 2026-08-04
A | bar: 2026-08-03 to 2026-08-04
| Station - 3 : T10RH | P | [184 empty] | 0 | bar: 2026-08-05 to 2026-08-06
A | bar: 2026-08-05 to 2026-08-06
| Station - 4 : T10LH | P | [184 empty] | 0 | bar: 2026-08-07
A | bar: 2026-08-07
| Station - 5 : T20RH | P | [184 empty] | 0 | bar: 2026-08-10 to 2026-08-11
A | bar: 2026-08-10 to 2026-08-11
| Station - 6 : T20LH | P | [184 empty] | 0 | bar: 2026-08-12 to 2026-08-13
A | bar: 2026-08-12 to 2026-08-13
| Station - 7 : T20ENG | P | [184 empty] | 0 | bar: 2026-08-14
A | bar: 2026-08-14
| Station - 8 : T30RH | P | [184 empty] | 0 | bar: 2026-08-17 to 2026-08-18
A | bar: 2026-08-17 to 2026-08-18
| Station - 9 : T30LH | P | [184 empty] | 0 | bar: 2026-08-19 to 2026-08-20
A | bar: 2026-08-19 to 2026-08-20
| Station - 10 : T30ENG | P | [184 empty] | 0 | bar: 2026-08-21
A | bar: 2026-08-21
| Station - 11 : T40RH | P | [184 empty] | 0 | bar: 2026-08-24 to 2026-08-25
A | bar: 2026-08-24 to 2026-08-25
| Station - 12 : T50RH | P | [184 empty] | 0 | bar: 2026-08-26 to 2026-08-27
A
| Station - 13 : T50LH | P | [184 empty] | 0 | bar: 2026-08-28
A
| Station - 14 : T60ENG | P | [184 empty] | 0 | bar: 2026-08-31 to 2026-09-01
A
| Station - 15 : T70RH | P | [184 empty] | 0 | bar: 2026-09-02 to 2026-09-03
A
| Station - 16 : T70LH | P | [184 empty] | 0 | bar: 2026-09-04
A
| Station - 17 : T90RH | P | [184 empty] | 0 | bar: 2026-09-07 to 2026-09-08
A
| Station - 18 : T90LH | P | [184 empty] | 0 | bar: 2026-09-09 to 2026-09-10
A
| Station - 19 : C40RH | P | [184 empty] | 0 | bar: 2026-09-11
A
| Station - 20 : P10LH | P | [184 empty] | 0 | bar: 2026-09-14 to 2026-09-15
A
| Station - 21 : P20LH | P | [184 empty] | 0 | bar: 2026-09-16 to 2026-09-17
A
| Station - 22 : P30RH | P | [184 empty] | 0 | bar: 2026-09-18
A
| Station - 23 : P30LH | P | [184 empty] | 0 | bar: 2026-09-21 to 2026-09-22
A
| Station - 24 : C45RR | P | [184 empty] | 0 | bar: 2026-09-23 to 2026-09-24
A
| Station - 25 : R20 | P | [184 empty] | 0 | bar: 2026-09-25
A
| Station - 26 : C70 | P | [184 empty] | 0 | bar: 2026-09-28 to 2026-09-29
A
| Station - 27 : C80RH | P | [184 empty] | 0 | bar: 2026-09-30 to 2026-10-01
A
| Station - 28 : F10RH | P | [184 empty] | 0 | bar: 2026-10-02
A
| Station - 29 : F10LH | P | [184 empty] | 0 | bar: 2026-10-05 to 2026-10-06
A
| Station - 30 : F10ENG | P | [184 empty] | 0 | bar: 2026-10-07 to 2026-10-08
A
| Station - 31 : F20RH | P | [184 empty] | 0 | bar: 2026-10-09
A
| Station - 32 : F20LH | P | [184 empty] | 0 | bar: 2026-10-12 to 2026-10-13
A
| Station - 33 : F30RH | P | [184 empty] | 0 | bar: 2026-10-14 to 2026-10-15
A
| Station - 34 : F30LH | P | [184 empty] | 0 | bar: 2026-10-16
A
| Station - 35 : F40RH | P | [184 empty] | 0 | bar: 2026-10-19 to 2026-10-20
A
| Station - 36 : F40LH | P | [184 empty] | 0 | bar: 2026-10-21 to 2026-10-22
A
| Station - 37 : F60RH | P | [184 empty] | 0 | bar: 2026-10-23
A
| Station - 38 : F60LH | P | [184 empty] | 0 | bar: 2026-10-26 to 2026-10-27
A
| Station - 39 : F70RH | P | [184 empty] | 0 | bar: 2026-10-28 to 2026-10-29
A
| Station - 40 : F70LH | P | [184 empty] | 0 | bar: 2026-10-30
A
| Station - 41 : F80RH | P | [184 empty] | 0 | bar: 2026-11-02 to 2026-11-03
A
| Station - 42 : F80LH | P | [184 empty] | 0 | bar: 2026-11-04 to 2026-11-05
A
| Station - 43 : F90RH | P | [184 empty] | 0 | bar: 2026-11-06
A
| Station - 44 : F90LH | P | [184 empty] | 0 | bar: 2026-11-09 to 2026-11-10
A

## WPI Implementation Plan - O (3)
WPI Station Wise Assessment Timing Plan
|  | Year - 2026 | [156 empty] | Year - 2027
|  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | Sep'26 | [29 empty] | Oct'26 | [30 empty] | Nov'26 | [29 empty] | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
[5 empty] | WK27 |  |  |  |  | WK28 | [6 empty] | WK29 | [6 empty] | WK30 | [6 empty] | WK31 | [6 empty] | WK32 | [6 empty] | WK33 | [6 empty] | WK34 | [6 empty] | WK35 | [6 empty] | WK36 | [6 empty] | WK37 | [6 empty] | WK38 | [6 empty] | WK39 | [6 empty] | WK40 | [6 empty] | WK41 | [6 empty] | WK42 | [6 empty] | WK43 | [6 empty] | WK44 | [6 empty] | WK45 | [6 empty] | WK46 | [6 empty] | WK47 | [6 empty] | WK48 | [6 empty] | WK49
MEA |  | CM | SFM | [20 empty] | SHRM | [104 empty] | X1 | [28 empty] | 2026-12-01: X2; 2027-02-01: LRM / X3; 2027-03-01: PBM; 2027-04-01: BM/SOP
MEA |  | CM |  | SFM | [75 empty] | SHRM | [77 empty] | 2027-02-01: X1; 2027-03-01: X2; 2027-05-01: LRM/X3; 2027-06-01: PBM; 2027-07-01: BM/SOP
WPI LOOP |  | -2 | -1 |  | 0 | [81 empty] | 1 & 2 & 3 | [41 empty] | 4 | [28 empty] | 2027-03-01: 5
Activity Details |  |  |  | Date | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10
|  |  |  | Day | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Workstation Layout Readiness including Logistics flow |  |  |  | F: WPI Visit at RJN Pant; T: Workstation layout readiness & logistics flow assessment
JSRA risk assessment |  |  |  | W: Station wise Job Safety Risk Assessment
Papper Scroll Mapping |  |  |  | T: Station wise overall papper scroll mapping & actions convergence
O&R ( Lite PFMEA ) |  |  |  | T: Detailed station process wise O&R study with QCP
Proactive SQAM Assessment |  |  |  | F: Process wise SQAM assessment
Line Balancing Workshop ( VA & NVA assessment ) |  |  |  | T: Station wise Value Added & Non-Value added study & NVA Reduction opportunity identification
JES creation ( Digi JES with Conversion of Local language ) | [167 empty] | MZZCCHME8TV040854 9T | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Workstation Grid Validation | [167 empty] | 883QAB3023236 | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to T
Daily CFT Gemba Meeting ( 4:30 : 5:30 PM ) |  |  |  | M: *Daily Gemba connect with CFT - WPI Progress review | 849Q000009869
861YAA0024099 | bar: Day to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Station - 1 : Pilot Station ( C10 ) | P | bar: M to F; M to F; M to F
A | bar: M to F; M to F; M to F; M to F; M to F; M
Station - 2 : PBS | P | bar: M to F; M to F
A | bar: M to F
Station - 3 : T10RH | P | bar: M to F
A | bar: M to F; M to F
Station - 4 : T10LH | P | bar: M to F
A | bar: M to F
Station - 5 : T20RH | P | bar: M to F
A | bar: M to F; M to F
Station - 6 : T20LH | P | bar: M to F
A | bar: M to F
Station - 7 : T20ENG | P | bar: M to F
A | bar: M to F; M
Station - 8 : T30RH | P | bar: M to F
A | bar: M to F
Station - 9 : T30LH | P | bar: M to F
A | bar: M to F
Station - 10 : T30ENG | P | bar: M to F
A | bar: M to F
Station - 11 : T40RH | P | bar: M to F
A | bar: M to F
Station - 12 : T50RH | P | bar: M
A
Station - 13 : T50LH | P | bar: T
A
Station - 14 : T50ENG | P | bar: T
A
Station - 15 : T60ENG | P | bar: S
A
Station - 16 : T70RH | P | bar: M to T
A
Station - 17 : T70LH | P | bar: W
A
Station - 18 : T90RH | P | bar: T
A
Station - 19 : T90LH | P | bar: F to S
A
Station - 20 : C40RH | P | bar: M
A
Station - 21 : P10RH | P | bar: T to W
A
Station - 22 : P20LH | P | bar: T
A
Station - 23 : P30RH | P | bar: F
A
Station - 24 : P30LH | P | bar: S
A
Station - 25 : C45RR | P | bar: M to T
A
Station - 26 : R20 | P | bar: W
A
Station - 27 : C70 | P | bar: T
A
Station - 28 : C80RH | P | bar: S
A
Station - 29 : F10RH | P | bar: M
A
Station - 30 : F10LH | P | bar: W
A
Station - 31 : F10ENG | P | bar: T
A
Station - 32 : F20RH | P | bar: S
A
Station - 33 : F20LH | P | bar: M
A
Station - 34 : F30RH | P | bar: T
A
Station - 35 : F30LH | P | bar: W
A
Station - 36 : F40RH | P | bar: T
A
Station - 37 : F40LH | P | bar: F
A
Station - 38 : F60RH | P | bar: S
A
Station - 39 : F60LH | P | bar: M
A
Station - 40 : F70RH | P | bar: T
A
Station - 41 : F70LH | P | bar: W
A
Station - 42 : F80LH | P | bar: T
A
Station - 43 : F90RH | P | bar: F
A
Station - 44 : F90LH | P | bar: S
A
Today
100% Station Assessment Completion -WK48
Current Status :
- 80% Pilot Station Assessment Completed.
- O&R / SQAM & JSRA Reassessment Planned
- 100% Completion by 7th Aug

## STATION WISE PROGRESS
Station # | SAFETY |  | CUSTOMER EXPERIENCE |  | LOGISTICS | [5 empty] | WORKPLACE ORG. |  |  |  |  | WORKSTATION GRID | Completion %
| JSRA risk assessment | MURI ASSESMENT | O&R ( Lite PFMEA ) / Proactive SQAM | LLR / Mountability | Material classification study | Flow analysis | Workstation Area calculation | Parts stock management | Workstation Layout Readiness including Logistics flow | Papper Scroll Mapping | Process sequence analysis | Model matrix mapping | Line Balancing Workshop ( VA & NVA assessment ) | Spaghetti study | SCROLL DIAGRAM | Workstation Grid Validation
PBS | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T10RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Completed
T10LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Inprogress
T20RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Yet to start
T20LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T20ENG | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30ENG | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T40RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T50RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T50LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed |  | 93.75%
T50ENG | 2026-10-14 | Completed | 2026-10-15 | 2026-10-15 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 43.75%
T60ENG | 2026-10-15 | Completed | 2026-10-17 | 2026-10-17 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-17 | 2026-10-17 | 2026-10-17 | 2026-10-17 | 2026-10-17 | 2026-10-17 | 43.75%
T70RH | 2026-10-16 | Completed | 2026-10-20 | 2026-10-20 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 43.75%
T70LH | 2026-10-17 | Completed | 2026-10-22 | 2026-10-22 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 43.75%
T90LH | 2026-10-20 | Completed | 2026-10-23 | 2026-10-23 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 2026-10-23 | 43.75%
T90RH | 2026-10-21 | Completed | 2026-10-24 | 2026-10-24 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 43.75%
C10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
C40RH | 2026-10-21 | Completed | 2026-10-02 | 2026-10-02 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 43.75%
P10RH | 2026-10-21 | Completed | 2026-10-24 | 2026-10-24 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 43.75%
P20LH | 2026-10-22 | Completed | 2026-10-26 | 2026-10-26 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 43.75%
P30RH | 2026-10-22 | Completed | 2026-10-27 | 2026-10-27 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 43.75%
P30LH | 2026-10-22 | Completed | 2026-10-28 | 2026-10-28 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 43.75%
C45RR | 2026-10-23 | Completed | 2026-10-29 | 2026-10-29 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 43.75%
R20 | 2026-10-23 | Completed | 2026-10-30 | 2026-10-30 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 2026-10-30 | 43.75%
C70 | 2026-10-23 | Completed | 2026-11-02 | 2026-11-02 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 43.75%
C80RH | 2026-10-24 | Completed | 2026-11-03 | 2026-11-03 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-03 | 2026-11-03 | 2026-11-03 | 2026-11-03 | 2026-11-03 | 2026-11-03 | 43.75%
F10RH | 2026-10-24 | Completed | 2026-11-04 | 2026-11-04 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 43.75%
F10LH | 2026-10-24 | Completed | 2026-11-05 | 2026-11-05 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 43.75%
F10ENG | 2026-10-26 | Completed | 2026-11-06 | 2026-11-06 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 43.75%
F20RH | 2026-10-26 | Completed | 2026-11-10 | 2026-11-10 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 43.75%
F20LH | 2026-10-26 | Completed | 2026-11-11 | 2026-11-11 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 43.75%
F30RH | 2026-10-27 | Completed | 2026-11-12 | 2026-11-12 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 43.75%
F30LH | 2026-10-27 | Completed | 2026-11-13 | 2026-11-13 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 43.75%
F40RH | 2026-10-27 | Completed | 2026-11-16 | 2026-11-16 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 43.75%
GLUE | 2026-10-28 | Completed | 2026-11-17 | 2026-11-17 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-17 | 2026-11-17 | 2026-11-17 | 2026-11-17 | 2026-11-17 | 2026-11-17 | 43.75%
F60RH | 2026-10-28 | Completed | 2026-11-18 | 2026-11-18 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 43.75%
F60LH | 2026-10-28 | Completed | 2026-11-19 | 2026-11-19 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 43.75%
F70RH | 2026-10-29 | Completed | 2026-11-20 | 2026-11-20 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-11-20 | 2026-11-20 | 43.75%
F70LH | 2026-10-29 | Completed | 2026-11-23 | 2026-11-23 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 43.75%
F80LH | 2026-10-29 | Completed | 2026-11-24 | 2026-11-24 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 43.75%
F90LH | 2026-10-30 | Completed | 2026-11-25 | 2026-11-25 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 43.75%
F100RH | 2026-10-30 | Completed | 2026-11-26 | 2026-11-26 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 43.75%

## Sheet1
ddd
Count of OBSERVATION | Column Labels | [6 empty] | Grand Total | 263
Row Labels | CLOSED | INPROGRESS | Grand Total |  |  |  |  | CUSTOMER EXPERINCE | 158
CUSTOMER EXPERINCE | 109 | 49 | 158 |  | 68.99% |  |  | WORK PLACE ORGANISATION | 66
HEALTH & SAFETY | 2 | 21 | 23 |  | 8.696% |  |  | HEALTH & SAFETY | 23
LOGISTIC | 1 | 15 | 16 |  | 6.25% |  |  | LOGISTIC | 16
WORK PLACE ORGANANISATION | 2 | 64 | 66 |  | 3.03%
Grand Total | 114 | 149 | 263
[11 empty] | Closed | Inprogress
[11 empty] | Closed | Inprogress
[10 empty] | CUSTOMER EXPERINCE | 109 | 49
| Column Labels | [8 empty] | HEALTH & SAFETY | 2 | 21
| FACILITY | PART | PROCESS | STANDRAD | TRAINING | (blank) | Grand Total |  |  | WORKPLACE ORGANISATION | 2 | 64
Count of OBSERVATION | 36 | 6 | 23 | 10 | 11 | 177 | 263 |  |  | LOGISTIC | 1 | 15
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## OBSERVATION TRACKER
SL. NO. | STATION NO | Observation Date | STANDARD CRETERIA | ACTIVITY | KPI | OBSERVATION | PHOTO | BEFORE O&R LEVEL | ACTION DETAILS | ACTION CATEGREY | RESP. LEAD | SUPPORTING PILOT | TARGET DATE | TARGET WK | O&R LEVEL ( AFTER ACTION ) | STATUS
1 | C10 ( PILOT ) | WK29 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | CLIPPING TIME FINGER GOT INJURY - NO GLOVES |  | N/A | PU GLOVES IMPLEMENTED AT POF | TRAINING | DAVID MESHACK |  | 2026-07-20 | WK30 | N/A | CLOSED
2 | C10 ( PILOT ) | WK29 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | FUEL TANK GUN PICKING - TRUNCK FLEXION , SHOULDER FLEXION & LATERAL , HEAD FLEXION , MORE WALK & |  | N/A | NEED TO VALIDATION ON SAFETY | FACILITY | DAVID MESHACK |  | 2026-09-25 | WK38 | N/A | INPROGRESS
3 | C10 ( PILOT ) | WK29 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | U/B PLUG ON BOTTOM TUNNEL - TEUNCK FLEXION , SHOULDER FLEXION , HEAD FLEXION , ELBOW ANGULATION , MORE WALK |  | N/A | NEED TO VALIDATION ON SAFETY | FACILITY | DAVID MESHACK |  | 2026-09-25 | WK38 | N/A | INPROGRESS
4 | C10 ( PILOT ) | WK29 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | FUEL TANK ASSY - MANUAL PUSHING BY LEG - LIFTING ASSIST |  | N/A | FUEL TANK LIFTER TO BE SYNCHRONISED WITH HANGER (OR) FUEL TANK & BATTERY LIFTER TO BE COMMONISED | FACILITY | DAVID MESHACK |  | 2026-08-27 | WK35 | N/A | INPROGRESS
5 | C10 ( PILOT ) | WK29 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | TRIP HAZARD PART PICKING ( PLATFORM ) |  | N/A | RAIL TO BE CLOSED TO AVOID TRIP | FACILITY | DAVID MESHACK |  | 2026-08-27 | WK35 | N/A | INPROGRESS
6 | C10 ( PILOT ) | WK29 | CUSTOMER EXPERINCE | O&R | DIVERSITY | BRAKE PIPE LH MORE THAN 4 SPEC CURRENT O&R LEVEL O - ?? / R - ?? |  | 1 | CURRENT CONTROL : FAV PCA PROPOSAL : PICK TO LIGHT TO BE PROVIDE AFTER O&R LEVEL : O - ?? / R - ?? | FACILITY | SENTHIL SUBBARAYAN |  | 2026-12-24 | WK52 | 3 | INPROGRESS
7 | C10 ( PILOT ) | WK29 | CUSTOMER EXPERINCE | O&R | DIVERSITY | BRAKE PIPE RH MORE THAN 4 SPEC |  | 1 | CURRENT CONTROL : FAV PCA PROPOSAL : PICK TO LIGHT TO BE PROVIDE | FACILITY | SENTHIL SUBBARAYAN |  | 2026-12-24 | WK52 | 3 | INPROGRESS
8 | C10 ( PILOT ) | WK29 | CUSTOMER EXPERINCE | O&R | DIVERSITY | B MOUNT MORE THEN 4 SPEC |  | 1 | CURRENT CONTROL : FAV PCA PROPOSAL : PICK TO LIGHT TO BE PROVIDE | FACILITY | SENTHIL SUBBARAYAN |  | 2026-12-24 | WK52 | 3 | INPROGRESS
9 | C10 ( PILOT ) | WK29 | CUSTOMER EXPERINCE | O&R | DIVERSITY | PARKING CABLE MORE THAN 4 SPEC |  | 1 | CURRENT CONTROL : FAV PCA PROPOSAL : PICK TO LIGHT TO BE PROVIDE | FACILITY | SENTHIL SUBBARAYAN |  | 2026-12-24 | WK52 | 3 | INPROGRESS | Catagry
10 | C10 ( PILOT ) | WK30 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | LAYOUT | START / END MARK NOT AVAILABLE IN STATION - GREEN , ORANGE / RED ZONE MARK NOT AVAILABLE |  | N/A | STATION LAYOUT MARKING TO BE DONE | FACILITY | DAVID MESHACK |  | 2026-08-08 | WK32 | N/A | INPROGRESS
11 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ECC21 RUBBER PPLUG NOT FIX PROPERLY |  | 1 | NEIGHBOUR CHECK POINT IN C20 | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK34 | 1 | CLOSED
12 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | BRAKE PIPE NOT LOCK TO CLIP |  | 1 | BRAKE PIPE LOCKING CONFIRMATION IN C40B JES | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK35 | 5 | CLOSED
13 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUEL TANK MOUNTING BOLT NOT MOUNT |  | 3 | JES CHECK POINT ADD IN C20 | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK35 | 5 | CLOSED
14 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUEL TANK CONNECTOR SNAP NOT SNAP |  | 1 | KEY POINT ADD IN SNAP LOCK CONFERMATION IN JES | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK35 | 3 | CLOSED
15 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PARKING CABLE GROMMET NOT LOCKING |  | 1 | NEIGHBOUR CHECK TO BE ADD IN C40 RH & LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK35 | 3 | CLOSED
16 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PARKING CABLE CLIP NOT LOCKING |  | 1 | NEIGHBOUR CHECK TO BE ADD IN C20LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-20 | WK35 | 3 | CLOSED
17 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PKB CABLE NOT LOCK |  | 1 | PULL CHECK IN POF & NEIGHBOUR CHECK TO BE ADD IN C40 RH & LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-08-21 | WK36 | 3 | CLOSED
18 | C10 ( PILOT ) | WK31 | CUSTOMER EXPERINCE | TOOLS & EQUIPMENT | FACILITY | DC TOOL NOT CONSIDERED FOR A SAFETY-CRITICAL PROCESS (ABS PROCESS WAS SHIFTED FROM TRIM TO CHASSIS DUE TO THE LHD DESIGN CHANGE) |  | 1 | DC TOOL TO BE PROVIDED | FACILITY | SENTHIL SUBBARAYAN |  | 2026-12-24 | WK52 | 5 | INPROGRESS
19 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | ADDITION OF ABS PROCESS INCREASING TOTAL STATION’S TAKT TIME |  | N/A | LHD Process addition to be capture in Line balancing | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-11-02 | WK45 | N/A | INPROGRESS
20 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VA & NVA STANDARD TO ACTUAL MISMATCH |  | N/A | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | PROCESS | SENTHIL SUBBARAYAN |  | 2026-11-02 | WK45 | N/A | INPROGRESS
21 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOK DUE TO AS PER SOS NOT FOLLOWED |  | N/A | PROCESS SEQUENCE FLOW NEED TO COACH TO MEMBER | TRAINING | DAVID MESHACK |  | 2026-08-22 | WK34 | N/A | INPROGRESS
22 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SPARE WHEEL HANGER PROCESS NOT MENTIONED IN C10 SOS |  | N/A | NEED TO POCESS ADD IN SOS | STANDRAD | DAVID MESHACK |  | 2026-08-22 | WK34 | N/A | INPROGRESS
23 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | BOTH BRAKE PIPE PICKING DIFFICULT DUE TO MORE QUANTITY FEEDING IN RACK |  | N/A | FIFO TO BE MAINTAIN IN BRAKE PIPE FEEDING LHD PART RACK TO PLACE IN C10 FUEL TANK PART MOVE TO RECAD (ILE SUPPORT) | FACILITY | SENTHIL SUBBARAYAN | JEROME | 2026-08-25 | WK35 | N/A | INPROGRESS
24 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | (OPERATOR INTERFERANCE) DUE TO C20 PROCESS NOT ABLE TO DO THE PROCESS IN C20 |  | N/A | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | PROCESS | SENTHIL SUBBARAYAN |  | 2026-11-02 | WK45 | N/A | INPROGRESS
25 | C10 ( PILOT ) | WK32 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FUEL TANK SUB ASSY DIFFICULT DUE TO PLATFROM DISTRUB |  | N/A | FUEL TANK PROCESS ALLOCATION CHANGE TO C10 TO C20 LINE BALANCING STUDY AND SAFETY POINT VALIDATE | PROCESS | SENTHIL SUBBARAYAN |  | 2026-11-02 | WK45 | N/A | INPROGRESS
26 | C10 ( PILOT ) | WK31 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES NOT AVILABLE : 2 |  | N/A | JES TO BE CREATE CONVERT LOCAL LANGUAGE | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-08-20 | WK34 | N/A | INPROGRESS
27 | C10 ( PILOT ) | WK31 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN HOW TO DO : 6 |  | N/A | JES TO BE RE-VAMP AND ADD CONVERT LOCAL LANGUAGE | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-08-20 | WK34 | N/A | INPROGRESS
28 | C10 ( PILOT ) | WK31 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN KEY POINT : 2 |  | N/A | JES TO BE RE-VAMP AND ADD CONVERT LOCAL LANGUAGE | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-08-20 | WK34 | N/A | INPROGRESS
29 | C10 ( PILOT ) | WK31 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN OK / NOK PICTURE : 5 |  | N/A | OK / NOK PICTURE TO BE ADD | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-08-20 | WK34 | N/A | INPROGRESS
30 | C10 ( PILOT ) | WK31 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN VARIANT AND BOM : 5 |  | N/A | JES TO BE RE-VAMP | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-08-20 | WK34 | N/A | INPROGRESS
31 | C10 ( PILOT ) | WK34 | LOGISTIC | PAPER SCROLL | LAYOUT | BRAKE PIPE PART LH OUTOFF IN STATION |  | N/A | NEED TO GAPE VALIDATION | PROCESS | SENTHIL SUBBARAYAN | JEROME | 2026-11-02 | WK45 | N/A | INPROGRESS
32 | C10 ( PILOT ) | WK34 | LOGISTIC | PAPER SCROLL | LAYOUT | BRAKE PIPE PART RH OUTOFF IN STATION |  | N/A | NEED TO GAPE VALIDATION | PROCESS | SENTHIL SUBBARAYAN | JEROME | 2026-11-02 | WK45 | N/A | INPROGRESS
33 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD STAY ROD NOT LOCK WITH HOOD GROMMET |  | 1 | NEIGHBOUR CHECK POINT IN T20ENG STATION | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
34 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ALL DOOR SEALED GROMMET MISS |  | 1 | NEIGHBOUR CEHCK POINT ADD IN T70LH,T90LH,T90RH & T100RH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
35 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ALL DOOR STOPPER MISS |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
36 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SILL PLUG MISS IN RH & LH |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
37 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PLR GROMMET MISS IN RH & LH |  | 1 | C PLR SCREW TIGHT TIME CHECK THE GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
38 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | TYRE PRESSURE LABLE MISS |  | 3 | NEIGHBOUR CHECK POINT IN T40RH AND PENCIL MARK APPLY | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 5 | CLOSED
39 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CHARGE DOOR NOT TIGHTEN |  | 1 | NEIGHBOUR CHECK POINT IN T70TG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 5 | CLOSED
40 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VEHICLE DOLLY WHEEL HARD |  | N/A | AGV CONCEPT | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
41 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | HARNESS PICKING UNWANTED WALK |  | N/A |  | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
42 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WALK PATH MORE DUE TO RH SIDE PART PICK |  | N/A | NEED TO ARRANGE THE PART RACK | FACILITY | SENTHIL SUBBARAYAN | RAJA J | 2026-09-10 | WK36 | N/A | INPROGRESS
43 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VEHICLE NOT PUSH ON PAINT SHOP |  | N/A | AGV CONCEPT | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
44 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VEHCILE NOT ABLE TO MOVE ON TACK DUE TO FLOOR DAMGE |  | N/A | SAFETY | FACILITY | DAVID MESHACK | KRISHNAKUMAR SUBBAIAH |  |  | N/A | INPROGRESS
45 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | DOOR SLEDGE TOOL REMOVING DIFFICULT |  | N/A | PAINT | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
46 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | PLACE THE HARNESS PROCESS MISS IN PBS SOS |  | N/A | NEED TO ADD THE HARNESS PROCESS IN SOS | STANDRAD | DAVID MESHACK |  | 2026-09-10 | WK36 | N/A | INPROGRESS
47 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | RH SIDE DOING PROCESS SEQUENCE MISMATCH |  | N/A | PROCESS SEQUENCE FLOW NEED TO COACH TO MEMBER | TRAINING | DAVID MESHACK |  | 2026-09-10 | WK36 | N/A | INPROGRESS
48 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VA & NVA STANDARD TO ACTUAL MISMATCH |  | N/A | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
49 | PBS | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | PBS STATION LOTS OF WALK PATH |  | N/A | PROCESS ALLOCATION | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
50 | PBS | WK34 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN HOW TO DO : 19 |  | N/A | JES TO BE RE-VAMP AND ADD CONVERT LOCAL LANGUAGE | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-09-06 | WK34 | N/A | INPROGRESS
51 | PBS | WK34 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN KEY POINT : 5 |  | N/A | JES TO BE RE-VAMP AND ADD CONVERT LOCAL LANGUAGE | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-09-06 | WK34 | N/A | INPROGRESS
52 | PBS | WK34 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN OK / NOK PICTURE : 1 |  | N/A | OK / NOK PICTURE TO BE ADD | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-09-06 | WK34 | N/A | INPROGRESS
53 | PBS | WK34 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | JES | JES - ISSUE IN VARIANT AND BOM : 1 |  | N/A | JES TO BE RE-VAMP | STANDRAD | DAVID MESHACK | PRAVEEN KUMAR PERUMAL | 2026-09-06 | WK34 | N/A | INPROGRESS
54 | PBS | WK34 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | SKID MOVEMENT FROM STROAGE TO PBS OUT STATION - TRUNCK ISSUES |  | N/A | Electric puller to be provide or Auto Transfer conveyor to be provide | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
55 | PBS | WK34 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | VEHICLE PULL AND PUSH TRUNCK ISSUE |  | N/A | Electric puller to be provide or Auto Transfer conveyor to be provide | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
56 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD STAY ROD NOT LOCK WITH HOOD GROMMET |  | 1 | NEIGHBOUR CHECK POINT IN T20ENG STATION | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
57 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ALL DOOR SEALED GROMMET MISS |  | 1 | NEIGHBOUR CEHCK POINT ADD IN T70LH,T90LH,T90RH & T100RH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
58 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ALL DOOR STOPPER MISS |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
59 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SILL PLUG MISS IN RH & LH |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
60 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PLR GROMMET MISS IN RH & LH |  | 1 | C PLR SCREW TIGHT TIME CHECK THE GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 3 | CLOSED
61 | PBS | WK34 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | TYRE PRESSURE LABLE MISS |  | 3 | NEIGHBOUR CHECK POINT IN T40RH AND PENCIL MARK APPLY | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-03 | WK35 | 5 | CLOSED
62 | T10RH | WK34 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE COMBI LAMP CLIP FIX TIME WALK STEP TO SLIP ON FENZ |  | N/A | NEED TO REMOVE THE FENZ SUPPORTER | FACILITY | SENTHIL SUBBARAYAN |  |  | WK38 |  | INPROGRESS
63 | T10RH | WK34 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE CURTAIN AIRBAG FIX TIME SPOTED BURR PRICKING ON FINGER |  | N/A | TO BE VALIDATION ON BIW PROCESS AND CONTROL | PROCESS | DAVID MESHACK |  |  | WK38 |  | INPROGRESS
64 | T10RH | WK34 | LOGISTIC | PAPER SCROLL | LOGISTIC | APERATURE PROTECTOR OUTOFF STATION |  | N/A | LOCATION CHANGE ON WITH IN LAYOUT | FACILITY | SENTHIL SUBBARAYAN |  |  | WK38 |  | INPROGRESS
65 | T10RH | WK34 | LOGISTIC | PAPER SCROLL | LOGISTIC | COMBI LAMP CLIP OUTOFF STATION |  | N/A | PROVIDED TO POUCH | FACILITY | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 |  | INPROGRESS
66 | T10RH | WK34 | LOGISTIC | PAPER SCROLL | LOGISTIC | STICKERS OUTFF STATION |  | N/A | NEED TO PROCESS ALLOCATION CHANGE | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 |  | INPROGRESS
67 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CAR BODY NOT SEATED PROPERLY |  | 1 | CONVEYOR PITCH NEED TO VERIFY | FACILITY | SENTHIL SUBBARAYAN |  |  | WK38 | 3 | CLOSED
68 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | COMBI LAMP CLIP MISS CC21 |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
69 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | COMBI LAMP CLIP MISS CC22 |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
70 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | COMBI LAMP CLIP MISS CC24 |  | 1 | CHECK POINT ADDED IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
71 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | QTR PANEL 25 DIA STICKER MISS |  | 1 | NEIGHBOUR CHECK POINT IN T60ENG WHILE BUMPER BRKT FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
72 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR BUMPER 40 DIA STICKER MISS |  | 1 | NEIGHBOUR CHECK POINT IN T60ENG WHILE BUMPER BRKT FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
73 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR GLASS RUNNER NOT LOCK PROPERLY IN SASH AREA |  | 1 | CHECK POINT PQG DOOR RUNNER PROPERLY LOCKING IN SASH AREA | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
74 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR GLASS RUNNER NOT LOCK IN DOOR PAMEL |  | 1 | CHECK POINT PQG DOOR RUNNER PROPERLY LOCKING IN DOOR PANEL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
75 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR GLASS RUNNER INSIDE NOT ADJUST |  | 1 | NEIGHBOUR CHECK POINT IN T70RH WHILE FRT DOOR GLASS FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
76 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR CHECKER ARM NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T20RH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
77 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | B PILLAR RAMP BRKT MISS |  | 1 | NEIGHBOUR CHECK POINT IN T70RH WHILE HEADLINER FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
78 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | B PILLAR NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T70RH WHILE HEADLINER FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
79 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PILLAR RAMP BRKT MISS |  | 1 | NEIGHBOUR CHECK POINT IN T70RH WHILE HEADLINER FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
80 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PILLAR NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T70RH WHILE HEADLINER FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
81 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR CHECKER ARM NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T20RH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
82 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CURTAIN AIRBAG NOT LOCATE PROPERLY |  | 1 | NEIGHBOUR CHECK POINT IN T30RH WHILE AIRBAG TIGHT TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
83 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CURTAIN AIRBAG CLIP NOT FIX PROPERLY |  | 1 | NEIGHBOUR CHECK POINT IN T50RH WHILE RC TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
84 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR GLASS RUNNER NOT LOCK IN DOOR PAMEL |  | 1 | CHECK POINT PQG DOOR RUNNER PROPERLY LOCKING IN DOOR PANEL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
85 | T10RH | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR GLASS RUNNER INSIDE NOT ADJUST |  | 1 | NEIGHBOUR CHECK POINT IN T90RH WHILE FRT DOOR GLASS FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-03 | WK38 | 3 | CLOSED
86 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | CC24 RR DOOR RUNNER PICKING MORE WALK |  | N/A | RACK MODIFICATION | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
87 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | CC22 RR DOOR RUNNER PICKING MORE WALK |  | N/A | RACK MODIFICATION | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
88 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | CC24 COMBI LAMP 2 WAY CLIP FIX TIME MORE TIME TAKE |  | N/A | TO BE CONFIRM WITH 4:30 MEATING | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
89 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WHILE KITTING PART PICKING TIME MORE DUE TO PART LOCATION CHANGE TO PLACE |  | N/A | TRAINING TO FEEN TO CRT LOCATION | FACILITY | SENTHIL SUBBARAYAN |  | 2026-10-03 | WK38 | N/A | INPROGRESS
90 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VA & NVA STANDARD TO ACTUAL TIME MISMATCH |  | N/A | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | PROCESS | SENTHIL SUBBARAYAN | RAJA J |  |  | N/A | INPROGRESS
91 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | KITTING PART PICKING PROCESS SOS MISSING |  |  |  | STANDRAD | DAVID MESHACK |  | 2026-10-03 | WK38 |  | INPROGRESS
260 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | APERATURE PROTECTOR PICKING T10 TO T100 |  | N/A |  | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
92 | T10RH | WK34 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | GUN PICKING SOS MISSING |  |  |  | STANDRAD | DAVID MESHACK |  | 2026-10-03 | WK38 |  | INPROGRESS
93 | T10RH | WK34 | LOGISTIC | WORKSTATION AUDIT | LAYOUT | WHILE PROCESS DOING PART FLOW NOK |  |  |  | FACILITY | SENTHIL SUBBARAYAN | JEROME |  |  |  | INPROGRESS
94 | T10LH | WK36 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE COMBI LAMP CLIP FIX TIME WALK STEP TO SLIP ON FENZ |  | N/A | NEED TO REMOVE THE FENZ SUPPORTER | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
95 | T10LH | WK36 | LOGISTIC | PAPER SCROLL | LOGISTIC | FASTNER LOCATION OUT OFF STATION |  | N/A | NEED TO ARRANGE WITHIN LAYOUT | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
96 | T10LH | WK36 | LOGISTIC | PAPER SCROLL | LOGISTIC | GLASS RUNNER OUT OFF STATION |  | N/A | NEED TO ARRANGE WITHIN LAYOUT | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
97 | T10LH | WK36 | LOGISTIC | PAPER SCROLL | LOGISTIC | PROTECTOR OUT OFF STATION |  | N/A | NEED TO ARRANGE WITHIN LAYOUT | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
98 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SPRING CLIP NOT LOCK PROPERLY |  | 1 | SPACIAL TOOL PROVIED TO CLIP LOCKING | FACILITY | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
99 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUEL DOOR CLIP MISS |  | 1 | NEIGHBOUR CHECK POINT IN T10ENG WHILE FUEL PLUNGER ASSEMBLE TIME CHECK | STANDRAD | DAVID MESHACK | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
100 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUEL DOOR NOT TIGHT |  | 1 | AFTER FUEL DOOR TIGHT THEN CONFIRMATION ON DOOR TIGHTEN IN T10TG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
101 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT LH DOOR GLASS RUNNER NOT LOCK IN SASH AREA |  | 1 | CHECK THE DOOR RUNNER PROPERLY LOCKING ON SASH PANEL IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
102 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT LH DOOR GLASS RUNNER NOT LOCK IN DOOR PANEL |  | 1 | DOOR RUNNER PROPERLY SEATED ON DOOR PANEL CHECK IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
103 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR GLASS RUNNER INNER NOT ADJUST IN PANEL |  | 1 | NEIGHBOUR CHECK POINT IN T70RH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
104 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT LH CHECKER BIW NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T20LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
105 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ANTENNA HARNESS MISS |  | 1 | NEIGHBOUR CHECK POINT IN T50LH WHILE ANTENNA ROD ASSEMBLE TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
106 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ANTENNA CONNECTOR STRUCK IN DASH INSULATIOR |  | 1 | NEIGHBOUR CHECK POINT IN T20LH WHILW DASH INSULATOR FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
107 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR LH CHECKER BIW NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T20LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
108 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | B PILLAR RAMP BRKT MISS LH SIDE |  | 1 | LH SIDE CURTAIL AIRBAG PROCESS NEED TO CHANE TO T50LH TOM T10LH | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
109 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | B PILLAR RAMP BRKT NOT TIGHT |  | 1 | LH SIDE CURTAIL AIRBAG PROCESS NEED TO CHANE TO T50LH TOM T10LH | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
110 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PILLAR RAMP BRKT MISS LH SIDE |  | 1 | LH SIDE CURTAIL AIRBAG PROCESS NEED TO CHANE TO T50LH TOM T10LH | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
111 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | C PILLAR RAMP BRKT NOT TIGHT |  | 1 | LH SIDE CURTAIL AIRBAG PROCESS NEED TO CHANE TO T50LH TOM T10LH | PROCESS | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
112 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR LH DOOR GLASS RUNNER NOT LOCK IN SASH AREA |  | 1 | DOOR RUNNER PROPERLY SEATED ON DOOR PANEL IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
113 | T10LH | WK36 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR GLASS RUNNER INNER NOT ADJUST IN PANEL |  | 1 | NEIGHBOUR CHECK POINT IN T90RH WHILE DOOR GLASS ASSEMBLE TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-02 | WK40 | 3 | CLOSED
114 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FUEL DOOR CLIP FIX TIME MORE WALK |  | N/A | LAYOUT TO BE MODIFICATION | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
115 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SEQUENCENOT FOLLOWED |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
116 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WALK PATH 18 STEP WHILE RR DOOR GLASS RUNNER |  | N/A | NEW RACK TO BE MODIFICATION | PROCESS | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
117 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FASTNER PICKING MISSING IN SOS |  | N/A | LAYOUT TO BE MODIFICATION | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
118 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | PART PICKING MISSING IN SOS |  |  |  | STANDRAD | DAVID MESHACK |  |  |  |  | INPROGRESS
261 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | APERTURE PROTECTOR PICKING T10 TO T100 |  | N/A |  | FACILITY | DAVID MESHACK |  |  |  | N/A | INPROGRESS
119 | T10LH | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | GUN PICKING MISSING IN SOS |  |  |  | STANDRAD | DAVID MESHACK |  |  |  |  | INPROGRESS
120 | T20RH | WK35 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | HARNESS SNAP AREA CABLE STRAP EXCESS |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
121 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUEL CABLE NOT INSERT |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE CABLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
122 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | TAILGATE OPENING CABLE NOT INSERT |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE CABLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
123 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PLUG MISSING |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE CABLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
124 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ECC21 FLOOR STICKER MISS |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE PLUG & STICKER | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
125 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DASH INSULATOR MTG CLIP MISS |  | 1 | WHILE BRAKE PEDAL FIX TIME CHECK THE CLIP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
126 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | A PILLAR INSULATOR MISS |  | 1 | WHILE DOOR HARNESS ROUTE TIME CEHCK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
127 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | A PILLAR MTG CLIP MISS |  | 1 | WHILE BRAKE PEDAL FIX TIME CHECK THE CLIP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
128 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD RELEASE CABLE MISS |  | 1 | WHILE HOOD RELEASE CABLE ROUTE BEFORE CHECK T30ENG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
129 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HLLD CABLE MISS |  | 1 | WHILE HLLD CABLE ROUTE BEFORE CHECK T30ENG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
130 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HVAC UNIT NOT TIGHTEN |  | 1 | WHILE DOOR ROUTING TIME CHECK THE HVAC MOUNTING | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
131 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HVAC DRAIN HOSE NOT INSERT |  | s | WHILE FLOOR CARPET INSERT BOTTOM ON HVAC TIME CHECK THE HOSE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
132 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT RH HANDLE NOT TIGHT |  | 1 | WHILE DOOR LATCH LINK ROD FIX TIME CHECK THE HANDLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
133 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR RH HANDLE NOT TIGHT |  | 1 | WHILE DOOR LATCH LINK ROD FIX TIME CHECK THE HANDLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
134 | T20RH | WK37 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR FLOOR PLUG MISS |  | 1 | WHILE SBR HARNESS ROUTING TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
135 | T20RH | WK35 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOT FOLLOWED |  | NA | TRAINING GIVEN TO MEMBER TO FOLLOW ON SEQUENCE WITH JIT METHOD | TRAINING | DAVID MESHACK |  | 2026-09-24 | WK40 | NA | CLOSED
136 | T20RH | WK35 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | PLUG ASSEMBLE PROCESS TAKE MORE TIME |  | NA | NEED TO PROPER TRINING GIVENT O TEAM MEMBER | PROCESS | SENTHIL SUBBARAYAN |  | 2026-09-30 | WK40 | N/A | INPROGRESS
137 | T20RH | WK35 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | VA & NVA STANDARD TO ACTUAL MISMATCH |  | N/A | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | PROCESS | SENTHIL SUBBARAYAN |  | 2026-11-02 | WK45 | N/A | INPROGRESS
138 | T20RH | WK35 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | PART PICKING NOT MENTION IN SOS |  | NA | NEED TO ADD THE PROCESS IN SOS | STANDRAD | DAVID MESHACK |  | 2026-09-30 | WK40 | 3 | CLOSED
139 | T20RH | WK35 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FUEL CABLE DIFFICULT TO INSERT |  | NA | PVC PIPE TO INSAERT TO PANEL CABLE TAKE OUT TIME NEED TI ADD | FACILITY | SENTHIL SUBBARAYAN |  |  | WK45 | N/A | INPROGRESS
140 | T20RH | WK35 | LOGISTIC | WORKSTATION AUDIT | LINE BALANCING | DASH INSULATOR PICKING MORE WALK |  | NA |  | FACILITY | SENTHIL SUBBARAYAN |  |  | WK45 |  | INPROGRESS
141 | T20ENG | WK35 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | HOOD SLEDGE TOOL FALL |  | NA |  | PROCESS | DAVID MESHACK |  |  |  |  | INPROGRESS
142 | T20ENG | WK35 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | LUGGAGE ROOM AREA BURR |  | NA |  | PROCESS | DAVID MESHACK |  |  |  |  | INPROGRESS
143 | T20ENG | WK35 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | HOOD SLEDGE TOOL REMOVE - ABOVE THE SHOLDER |  | NA |  |  | DAVID MESHACK |  |  |  |  | INPROGRESS
144 | T20ENG | WK35 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | 110 DIA HARNES COVER REMOVE TIME ELBOE HIT IN MEMBER FRAME |  | NA | HARNESS COVER REMOVE TAPE LESS IN SUPPLIER END | PROCESS | DAVID MESHACK |  |  |  |  | INPROGRESS
145 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | LH QTR PANEL STICKER MISS |  | 1 | WHILE QTR PANEL TRIM FIX TIME CHECK THE STICKER | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
146 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR BUMPER 40 DIA STICKER MISS |  | 1 | NEIGHBOUR CHECK POINT IN T70TG WHILE BUMPER BRKT FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
147 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | LUGGAGE ROOM PLUG MISS |  | 1 | CHECK POINT ADDED IN TRIM PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
148 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FIREWALL INSULATOR MISS & SPEC ERROR |  | 1 | NEED TO VISHUAL IN DIGITAL SYSTEM | FACILITY | DAVID MESHACK |  | WK48 | WK48 | 3 | INPROGRESS
149 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FIREWALL INSULATOR CLIP MISS |  | 1 | WHILE HLLD CABLE ROUTING TIME CHECK THE INSULATOR CLIP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
150 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | 2 WAY CLIP MISS |  | 1 | WHILE HLLD CABLE ROUTING TIME CHECK THE INSULATOR CLIP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
151 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUSE BOX BRKT MISS |  | 1 | FUSE BOX RC TIME CHECK THE BRACKET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
152 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FUSE BOX NOT TIGHT |  | 3 | FUSE BOX RC TIME CHECK THE BRACKET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 5 | CLOSED
153 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RH SIDE ENGINE ROOM HARNESS GROMMET NOT LOCK |  | 1 | AFTER LOCK THE GROMMET MARK APPLY IN GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
154 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | LH 110 DIA HARNESS GROMMET NOT LOCK |  | 1 | AFTER LOCK THE GROMMET MARK APPLY IN GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
155 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD OVER SLAM MISS RH |  | 1 | CHECK POINT ADDED IN TRIM PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
156 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD OVER SLAM MISS LH |  | 1 | CHECK POINT ADDED IN TRIM PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
157 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | USER RECOMMEND LABLE MISS |  | 1 | WHILE HOOD LATCH FIX TIME CHECK THE LABLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
158 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | USER RECOMMEND LABLE WRONGLY PASTE |  | 1 | CHECK POINT ADDED IN TRIM PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
159 | T20ENG | WK35 | LOGISTIC | PAPER SCROLL | LAYOUT | CC22,CC24 FIREWALL INSULATOR IS OUTOFF STATION |  | NA | LAYOUT TO BE MODIFICATION | PROCESS | SENTHIL SUBBARAYAN | JEROME |  |  |  | INPROGRESS
160 | T20ENG | WK35 | LOGISTIC | PAPER SCROLL | LAYOUT | SCANNING PROCESS IN RH SIDE |  | NA | LAYOUT TO BE MODIFICATION | PROCESS | SENTHIL SUBBARAYAN | JEROME |  |  |  | INPROGRESS
161 | T20ENG | WK35 | LOGISTIC | WORKSTATION AUDIT | LINE BALANCING | FIREWALL INSULATOR PROCESS MORE WALK STEP |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
162 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CC24 FIREWALL INSULATOR NOT ABLE TO ALIGN DUE TO STUD BEND |  |  |  | PART | YAMINI |  |  |  |  | CLOSED
163 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD OVER SLAM HARD TO ROTATE |  |  |  | PART | YAMINI |  |  |  |  | CLOSED
164 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RH 110 DIA GROMMET NOT LOCK WITH BIW |  |  |  | PART | YAMINI |  |  |  |  | CLOSED
165 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ECC21 110 DIA GROMMET NOT ABLE TO PULL |  |  |  | PART | YAMINI |  |  |  |  | CLOSED
166 | T20ENG | WK35 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PRESSURE SENSOR NOT ABLE TO FIX |  |  |  | PART | YAMINI |  |  |  |  | CLOSED
167 | T20LH | WK38 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE DOING PROCESS FEET PLACE ON CONVEYOR AND CHECKER PLATE DRAG THE LEG |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  | NA | INPROGRESS
168 | T20LH | WK38 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE HVAC TAKE TIME HIT ON PILLAR |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  | NA | INPROGRESS
169 | T20LH | WK38 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | CAR BODY APERATURE ARE BURR |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  | NA | INPROGRESS
170 | T20LH | WK38 | WORK PLACE ORGANANISATION | WORKSTATION AUDIT | LINE BALANCING | HVAC PICKING MORE WALIKING |  | NA |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  | NA | INPROGRESS
171 | T20LH | WK38 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FLOOR PLUG FIXING SEQUENCE NOT FOLLOWED |  | NA | STANDARD NEED TO BE FOLLOWED TO TRAINING GIVEN TO JIT METHOD | TRAINING | DAVID MESHACK |  | 2026-10-02 | WK40 | NA | INPROGRESS
172 | T20LH | WK38 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOT FOLLOWED |  | NA | STANDARD NEED TO BE FOLLOWED TO TRAINING GIVEN TO JIT METHOD | TRAINING | DAVID MESHACK |  | 2026-10-02 | WK40 | NA | INPROGRESS
173 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PLUG MISSING |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE CABLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
174 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ECC21 FLOOR STICKER MISS |  | 1 | WHILE FLOOR CARPET ASSEMBLE TIME CHCEK THE PLUG & STICKER | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
175 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DASH INSULATOR CLIP MISS |  |  | WHILE DASH PANEL HARNESS ROUTING TIME CHCEK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
176 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | A PILLAR INSULATOR MISS |  | 1 | WHILE DOOR HARNESS ROUTE TIME CEHCK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
177 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | A PILLAR MTG CLIP MISS |  | 1 | WHILE BRAKE PEDAL FIX TIME CHECK THE CLIP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
178 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT RH HANDLE NOT TIGHT |  | 1 | WHILE DOOR LATCH LINK ROD FIX TIME CHECK THE HANDLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
179 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR RH HANDLE NOT TIGHT |  | 1 | WHILE DOOR LATCH LINK ROD FIX TIME CHECK THE HANDLE | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
180 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HVAC NOT TIGHTEN |  | 1 | WHILE CCB ASSEMBLE TIME CHECK THE HVAC TIGHTEN | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
181 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HV CONNECTOR NOT CONNECT |  | 1 | WHILE HV CONNECTOR CONNECT TIME CHECK THE SECONDARY LOCK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
182 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PEPS BRKT NOT TIGHT |  | 1 | WHILE DOOR HARNESS ROUTING TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
183 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | PEPS ECU NOT TIGHT |  | 1 | WHILE DOOR HARNESS ROUTING TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
184 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR FLOOR PLUG MISS |  | 1 | NEIGHBOUR CHECK IN T20ENG WHILE LUGGAGE ROOM PLUG FIX TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
185 | T20LH | WK38 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR QTR AREA 25 STICKER MISS |  | 1 | WHILE QTR PANLE ROUTING TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-09-30 | WK40 | 3 | CLOSED
186 | T30LH | WK40 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE FLOOR CARPET PULLING DEKANEWTON - 40N |  | NA |  | PROCESS | DAVID MESHACK |  |  |  |  | INPROGRESS
187 | T30LH | WK40 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE WORKING IN CONVEYOR |  | NA | CONTROL PLAN IN CONVEYOR STOPAGE SYSTEM | FACILITY | DAVID MESHACK |  | 2026-09-29 | WK40 | NA | CLOSED
188 | T30LH | WK40 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | APERATURE ARE BURR |  | NA | SEATING TIME USING APERATURE FOAM | FACILITY | SENTHIL SUBBARAYAN | RAJA J | 2026-09-29 | WK40 | NA | INPROGRESS
189 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR HARNESS GROMMET NOT LOCK WITH BIW |  | 1 | CHECK POINT IN PQG WHILE CHECKER ARM RECHECK TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
190 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR ANTENA HARNESS ROUTING MISSING |  | 1 | NEIGHBOUR CHECK POINT IN T60LH WHILE DOOR GLASS ASSEMBLE TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
191 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR ANTENNA MISSING |  | 1 | NEIGHBOUR CHECK POINT ADDED IN T50LH CONNECTOR AND ANTENNA FIX | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
192 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR ANTENNA CONNECTOR NOT CONNECT |  | 1 | NEIGHBOUR CHECK POINT ADDED IN T50LH CONNECTOR AND ANTENNA FIX | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
193 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DOOR ANTENNA NOT FIX IN DOOR PANEL |  | 1 | NEIGHBOUR CHECK POINT ADDED IN T50LH CONNECTOR AND ANTENNA FIX | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
194 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SPEAKER GROMMET MISSING |  | 1 | NEIGHBOUR CHECK POINT IN T60LH | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
195 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SEAT CONNECTOR NOT PULL OUT FROM FLOOR CARPET |  | 1 | CHECK POINT IN PQG CONNECTO PULL OUT | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
196 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FLOOR CARPET VELCRO NOT PASTE |  | 1 | CHECK POINT IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
197 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | AIRBAG ECU NUT MISSING |  | 1 | NEIGHBOUR CHECK POINT ADDED IN T50 LH GSL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
198 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | AIRBAG ECU NOT TIGHTEN |  | 1 | NEIGHBOUR CHECK POINT ADDED IN T50 LH GSL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
199 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR REGULATOR MISS |  | 1 | NEIGHBOUR CHECK POINT IN T70LH WHILE DOOR GLASS FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
200 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR REGULATOR NUT MISSING |  | 1 | CHECK POINT IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
201 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR SPEAKER GROMMET NOT FIX |  | 1 | NEIGHBOUR CHECK POINT IN T60LH SPEAKER | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
202 | T30LH | WK40 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FLOOR CARPET NOT COME IN ON TIME |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
203 | T30LH | WK40 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOT FOLLOWED |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
204 | T30LH | WK40 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FUEL CABLE METAL STRIP NOT ABLE TO REMOVE |  | NA |  | PART | YAMINI |  |  |  | N/A | INPROGRESS
205 | T30LH | WK40 | LOGISTIC | WORKSTATION AUDIT | LINE BALANCING | AIRBAG ECU PART MORE DIVERSITY |  | 1 | PART COMING FROM KITTING | FACILITY | SENTHIL SUBBARAYAN |  | - | - | 3 | CLOSED
206 | T30LH | WK40 | LOGISTIC | WORKSTATION AUDIT | LINE BALANCING | PROCESS NOT DOING IN VEHICLE FLOW |  | NA | NEED TO BE TRAINING GIVEN TO PROCESS FLOW | PROCESS | SENTHIL SUBBARAYAN |  | 2026-10-06 | WK43 | 3 | INPROGRESS
207 | T30LH | WK40 | LOGISTIC | WORKSTATION AUDIT | LINE BALANCING | OPERATION DOING DOUBLE HANDLING TO PART |  |  |  | PROCESS | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
208 | T20ENG | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOT FOLLOWED |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
209 | T20ENG | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | REMOVE SLEDGE TOOL PROCESS MISSING IN SOS |  |  |  | STANDRAD | DAVID MESHACK |  |  |  |  | INPROGRESS
210 | T20ENG | WK36 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | 110 DIA HARNESS COVER REMOVE TIME MORE |  | NA | HARNESS DESIGN TO BE CHECK TO MASKIN TAPE | PROCESS | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
211 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | DASH PANEL HARNESS SNAP AFTER EASLY COMES OUT |  |  |  | PART | DAVID MESHACK |  |  |  |  | INPROGRESS
212 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | F08 FRT DOOR HARNESS HARD TO PULL |  |  |  | PART | DAVID MESHACK |  |  |  |  | INPROGRESS
213 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR REGULATOR NUT MISSING |  | 1 | CHECK POINT IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
214 | T30LH | WK40 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR REGULATOR MISS |  | 1 | NEIGHBOUR CHECK POINT IN T60LH WHILE DOOR GLASS FIX TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK43 | 3 | INPROGRESS
215 | T30ENG | WK40 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | WHILE FLOOR CARPET PICKING TIME FLT MOVEMENT |  |  |  | PROCESS | DAVID MESHACK |  |  |  |  | INPROGRESS
216 | T30ENG | WK40 | HEALTH & SAFETY | JSRA/ERGO | SAFETY | PROCESS DOING IN ENGINE COMPARTMENT BURR AVAILABLE IN FRAME |  |  |  | PROCESS | SENTHIL SUBBARAYAN | RAJA J |  |  |  | INPROGRESS
217 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT WASHER HOSE MISS |  | 1 | NEIGHBOUR CHECK POINT IN T50ENG WHILE RR WASHER HOSE ROUTING | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
218 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CMC BRKT MISS |  | 1 | WHILE HIGH PRESSURE FIX TIME CHCEK T50ENG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
219 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HLLD GROMMET NOT LOCK WIT BIW |  | 1 | NEIGHBOUR CHECK T40RH WHILE BRAKE PEDAL TIGHT TIME VERIFY THE HLLD GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
220 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RH SIDE HLLD CABLE NOT TAKE OUT |  | 1 | NEIGHBOUR CHCEK POINT IN C70 HEAD LAMP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
221 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | LH SIDE HLLD CABLE NOT TAKE OUT |  | 1 | NEIGHBOUR CHCEK POINT IN C70 HEAD LAMP | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
222 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CLIP MISSING ON HLLD |  | 1 | PQG CHCEK POINT ADDED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
223 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD RELEASE GROMMET NOT LOCK WITH BIW |  | 1 | NEIGHBOUR CHECK T40RH WHILE BRAKE PEDAL TIGHT TIME VERIFY THE HOOD RELEASE CABLE GROMMET | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
224 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CLIP MISSING ON HOOD RELEASE CABLE |  | 1 | PQG CHCEK POINT ADDED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
225 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HEATER PASS THROUGH MISSING |  | 1 | NEIGHBOUR CHCEK POINT IN T50ENG WHILE ABS ASSEMBLE TIME | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
226 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HEATER PASS THROUGH SCREW MISSING |  | 1 | CHECK POINT IN PQG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
227 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT FRAME GSAT SENSOR ROUTING MISSING |  | 1 | NEIGHBOUR CHCEK POINT IN T80TG WHILE HOOD LATCH RECECH TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
228 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | GSAT SENSOR CONNECTOR MISSING |  | 1 | NEIGHBOUR CHCEK POINT IN T80TG WHILE HOOD LATCH RECECH TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
229 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FLOOR CARPET SPEC ERROR |  | 1 | NEIGHBOUR CHECK POINT IN FLOOR CARPET T30RH & T50RH RC CLUTCH PEDAL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
230 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ENGINE COMPAERTMENT RH SIDE NOT TIGHT |  | 1 | WHILE RECHECK TIME CHECK T50ENG EARTHING | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
231 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ENGINE COMPAERTMENT LH SIDE NOT TIGHT |  | 1 | WHILE RECHECK TIME CHECK T50ENG EARTHING | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
232 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD RELEASE CABLE NOT LOCK WITH HOOD LATCH |  | 1 | NEIGHBOUR CHCEK POINT IN T80TG WHILE HOOD LATCH RECECH TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
233 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD LATCH NOT TIGHT |  | 1 | NEIGHBOUR CHCEK POINT IN T80TG WHILE HOOD LATCH RECECH TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 5 | INPROGRESS
234 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | VACCUM HOSE MISS |  | 1 | PICK TO LIGHT NEED TO BE PLACE | FACILITY | SENTHIL SUBBARAYAN |  |  |  |  | INPROGRESS
235 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | VACCUM HOSE CLIP NOT FIX IN DASH PANEL STUD |  | 1 | WHILE CLUTCH CABLE FIX TIME CHCEK T60ENG | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 3 | INPROGRESS
236 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CLUTCH PEDAL NOT TIGHT |  | 1 | NEIGHBOUR CHECK POINT IN T80TG CLUTCH PEDAL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 5 | INPROGRESS
237 | T30ENG | WK39 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CLUTCH CABLE NOT FIX |  | 1 | NEIGHBOUR CHECK POINT IN T70TG CLUTCH PEDAL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-06 | WK41 | 5 | INPROGRESS
238 | T30ENG | WK39 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | RC - FUSE BOX MISS IN SOS |  |  | ER3 PROCESS TIME CONFIRM TO DAVID & SENTHIL | STANDRAD | DAVID MESHACK |  |  |  |  | INPROGRESS
239 | T30ENG | WK39 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | RC - GSAT SENSOR PROCESS MISS IN SOS |  |  | ER3 PROCESS TIME CONFIRM TO DAVID & SENTHIL | STANDRAD | DAVID MESHACK |  |  |  |  | INPROGRESS
240 | T30ENG | WK39 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | HOOD JIG PROCESS TIME NOT ADD |  | NA | LINE BALANCING TO BE DONE ( IE ONBOARDING INPROGRESS ) | FACILITY | SENTHIL SUBBARAYAN |  |  |  | N/A | INPROGRESS
241 | T30ENG | WK39 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WIRING HARNESS MASKIN TAPE REMOVE TIME MORE |  | NA | CONFIRM TO DESIGN TEAM | PROCESS | SENTHIL SUBBARAYAN | RAJA J |  |  | N/A | INPROGRESS
242 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT RH DOOR STRICKER MISSING |  | 1 | WHILE AJAR SWITCH TIGHTEN TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
243 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR STRIKER NOT TIGHTEN |  | 1 | PQG CHCEK POINT ADDED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
244 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | FRT DOOR RH SPEAKER GROMMET MISSING |  | 1 | WHILE SPEAKER ASSEMBLE TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
245 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD RELEASE CABLE NOT TIGHTEN |  | 1 | WHILE CCB FIX TIME CHECK THE HOOD RELEASE CABLE MOUNTED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
246 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HOOD RELEASE CABLE NOT PLACE IN DASH PANEL |  | 1 | WHILE CCB FIX TIME CHECK THE HOOD RELEASE CABLE MOUNTED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
247 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | HARNESS NOT ROUTE IN A PILLAR AREA |  | 1 | WHILE CCB FIX TIME CHECK THE HOOD RELEASE CABLE MOUNTED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
248 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | CLUTCH PEDAL NOT TIGHTEN |  | 1 | WHILE RE CHECK TIME ENSURE TRHE CLUTCH PEDAL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
249 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | BRAKE PEDAL NOT TIGHTEN |  | 1 | WHILE RE CHECK TIME ENSURE TRHE BRAKE PEDAL | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
250 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ROOF FELT MISSING |  | 1 | WHILE ROOF ASSEMBLE TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
251 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | ROOF FELT NOT PASTE PROPERLY |  | 1 | WHILE ROOF ASSEMBLE TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
252 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR SPEAKER GROMMET NOT FIX ON DOOR |  | 1 | WHILE SPEAKER ASSEMBLE TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
253 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR STRIKER MISSING |  | 1 | WHILE AJAR SWITCH TIGHTEN TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
254 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | RR DOOR STRIKER NOT TIGHTEN |  | 1 | PQG CHCEK POINT ADDED | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
255 | T40RH | WK41 | CUSTOMER EXPERINCE | O&R | LLR / MOUNTABILITY | SBR HARNESS NOT ROUTING |  | 1 | WHILE RR SEAT BUCKLE TIGHTEN TIME CHECK | STANDRAD | SENTHIL SUBBARAYAN | RAJA J | 2026-10-12 | WK42 | 3 | CLOSED
256 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | SOS SEQUENCE NOT FOLLWED |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
257 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | FUEL LEVER TIGHTEN TIME MORE DUE TO WRONG GUN PICK |  | NA |  | TRAINING | DAVID MESHACK |  |  |  | N/A | INPROGRESS
258 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WHILE HARNESS TAPE REMOVE TIME MORE |  | NA |  | PART | DAVID MESHACK |  |  |  | N/A | INPROGRESS
259 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | RR DOOR SIDE MOVE TIME FASTENER PICK PLACE OIN FLOOR AREA WASTE TIME |  |  |  | TRAINING | DAVID MESHACK |  |  |  |  | INPROGRESS
262 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | WITH IN STATION PROCESS NOT DONE DUE TO FENZ DISTRUB |  | NA |  | FACILITY | DAVID MESHACK | KRISHNAKUMAR SUBBAIAH |  |  | N/A | INPROGRESS
263 | T40RH | WK41 | WORK PLACE ORGANANISATION | VA / NVA ANALYSIS | LINE BALANCING | DOOR PROTECTOR PICKING ON PBS TO F100 |  | NA |  | FACILITY |  |  |  |  | N/A | INPROGRESS

## STATION WISE PROGRESS (2)
Station # | SAFETY |  | CUSTOMER EXPERIENCE |  | LOGISTICS | [5 empty] | WORKPLACE ORG. |  |  |  |  | WORKSTATION GRID | Completion %
| JSRA risk assessment | MURI ASSESMENT | O&R ( Lite PFMEA ) / Proactive SQAM | LLR / Mountability | Material classification study | Flow analysis | Workstation Area calculation | Parts stock management | Workstation Layout Readiness including Logistics flow | Papper Scroll Mapping | Process sequence analysis | Model matrix mapping | Line Balancing Workshop ( VA & NVA assessment ) | Spaghetti study | SCROLL DIAGRAM | Workstation Grid Validation
PBS | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T10RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Completed
T10LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Inprogress
T20RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100% | Yet to start
T20LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T20ENG | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T30ENG | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T40RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T50RH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
T50LH | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-15 | 93.75%
T50ENG | 2026-10-22 | Completed | 2026-10-22 | 2026-10-22 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 2026-10-22 | 43.75%
T60ENG | 2026-10-24 | Completed | 2026-10-24 | 2026-10-24 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 2026-10-24 | 43.75%
T70RH | 2026-10-26 | Completed | 2026-10-26 | 2026-10-26 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 43.75%
T70LH | 2026-10-28 | Completed | 2026-10-28 | 2026-10-28 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 2026-10-28 | 43.75%
T90LH | 2026-10-30 | Completed | 2026-10-30 | 2026-10-30 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 2026-10-31 | 43.75%
T90RH | 2026-10-29 | Completed | 2026-10-29 | 2026-10-29 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 43.75%
C10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 100%
C40RH | 2026-11-02 | Completed | 2026-11-02 | 2026-11-02 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 2026-11-02 | 43.75%
P10RH | 2026-11-05 | Completed | 2026-11-05 | 2026-11-05 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 2026-11-05 | 43.75%
P20LH | 2026-11-03 | Completed | 2026-11-03 | 2026-11-03 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 2026-11-04 | 43.75%
P30RH | 2026-11-06 | Completed | 2026-11-06 | 2026-11-06 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 2026-11-06 | 43.75%
P30LH | 2026-11-07 | Completed | 2026-11-07 | 2026-11-07 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-07 | 2026-11-07 | 2026-11-07 | 2026-11-07 | 2026-11-07 | 2026-11-07 | 43.75%
C45RR | 2026-11-09 | Completed | 2026-11-09 | 2026-11-09 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 43.75%
R20 | 2026-11-11 | Completed | 2026-11-11 | 2026-11-11 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 2026-11-11 | 43.75%
C70 | 2026-11-12 | Completed | 2026-11-12 | 2026-11-12 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 2026-11-12 | 43.75%
C80RH | 2026-11-13 | Completed | 2026-11-13 | 2026-11-13 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 2026-11-13 | 43.75%
F10RH | 2026-11-16 | Completed | 2026-11-16 | 2026-11-16 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 43.75%
F10LH | 2026-11-18 | Completed | 2026-11-18 | 2026-11-18 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 2026-11-18 | 43.75%
F10ENG | 2026-11-19 | Completed | 2026-11-19 | 2026-11-19 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 2026-11-19 | 43.75%
F20RH | 2026-11-21 | Completed | 2026-11-21 | 2026-11-21 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-21 | 2026-11-21 | 2026-11-21 | 2026-11-21 | 2026-11-21 | 2026-11-21 | 43.75%
F20LH | 2026-11-23 | Completed | 2026-11-23 | 2026-11-23 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 2026-11-23 | 43.75%
F30RH | 2026-11-24 | Completed | 2026-11-24 | 2026-11-24 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 2026-11-24 | 43.75%
F30LH | 2026-11-25 | Completed | 2026-11-25 | 2026-11-25 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 2026-11-25 | 43.75%
F40RH | 2026-11-26 | Completed | 2026-11-26 | 2026-11-26 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 2026-11-26 | 43.75%
GLUE | 2026-11-27 | Completed | 2026-11-27 | 2026-11-27 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 2026-11-27 | 43.75%
F60RH | 2026-11-28 | Completed | 2026-11-28 | 2026-11-28 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-28 | 2026-11-28 | 2026-11-28 | 2026-11-28 | 2026-11-28 | 2026-11-28 | 43.75%
F60LH | 2026-11-30 | Completed | 2026-11-30 | 2026-11-30 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 2026-11-30 | 43.75%
F70RH | 2026-12-01 | Completed | 2026-12-01 | 2026-12-01 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 43.75%
F70LH | 2026-12-02 | Completed | 2026-12-02 | 2026-12-02 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-12-02 | 2026-12-02 | 2026-12-02 | 2026-12-02 | 2026-12-02 | 2026-12-02 | 43.75%
F80LH | 2026-12-03 | Completed | 2026-12-03 | 2026-12-03 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 2026-12-03 | 43.75%
F90LH | 2026-12-04 | Completed | 2026-12-04 | 2026-12-04 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-12-04 | 2026-12-04 | 2026-12-04 | 2026-12-04 | 2026-12-04 | 2026-12-04 | 43.75%
F100RH | 2026-12-05 | Completed | 2026-12-05 | 2026-12-05 | Completed | Completed | Completed | Completed | Completed | Completed | 2026-12-05 | 2026-12-05 | 2026-12-05 | 2026-12-05 | 2026-12-05 | 2026-12-05 | 43.75%

## WPI Implementation Plan - O (2) (hidden)
WPI Station Wise Assessment Timing Plan
|  | Year - 2026 | [156 empty] | Year - 2027
|  | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | Sep'26 | [29 empty] | Oct'26 | [30 empty] | Nov'26 | [29 empty] | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01
[5 empty] | WK27 |  |  |  |  | WK28 | [6 empty] | WK29 | [6 empty] | WK30 | [6 empty] | WK31 | [6 empty] | WK32 | [6 empty] | WK33 | [6 empty] | WK34 | [6 empty] | WK35 | [6 empty] | WK36 | [6 empty] | WK37 | [6 empty] | WK38 | [6 empty] | WK39 | [6 empty] | WK40 | [6 empty] | WK41 | [6 empty] | WK42 | [6 empty] | WK43 | [6 empty] | WK44 | [6 empty] | WK45 | [6 empty] | WK46 | [6 empty] | WK47 | [6 empty] | WK48 | [6 empty] | WK49
MEA |  | CM | SFM | [20 empty] | SHRM | [104 empty] | X1 | [28 empty] | 2026-12-01: X2; 2027-02-01: LRM / X3; 2027-03-01: PBM; 2027-04-01: BM/SOP
MEA |  | CM |  | SFM | [75 empty] | SHRM | [77 empty] | 2027-02-01: X1; 2027-03-01: X2; 2027-05-01: LRM/X3; 2027-06-01: PBM; 2027-07-01: BM/SOP
WPI LOOP |  | -2 | -1 |  | 0 | [81 empty] | 1 & 2 & 3 | [41 empty] | 4 | [28 empty] | 2027-03-01: 5
Activity Details |  |  |  | Date | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11
|  |  |  | Day | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Workstation Layout Readiness including Logistics flow |  |  |  | F: WPI Visit at RJN Pant; T: Workstation layout readiness & logistics flow assessment
JSRA risk assessment |  |  |  | W: Station wise Job Safety Risk Assessment
Papper Scroll Mapping |  |  |  | T: Station wise overall papper scroll mapping & actions convergence
O&R ( Lite PFMEA ) |  |  |  | T: Detailed station process wise O&R study with QCP
Proactive SQAM Assessment |  |  |  | F: Process wise SQAM assessment
Line Balancing Workshop ( VA & NVA assessment ) |  |  |  | T: Station wise Value Added & Non-Value added study & NVA Reduction opportunity identification
JES creation ( Digi JES with Conversion of Local language ) | [168 empty] | MZZCCHME8TV040854 9T | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Workstation Grid Validation | [168 empty] | 883QAB3023236 | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to T
Daily CFT Gemba Meeting ( 4:30 : 5:30 PM ) |  |  |  | M: *Daily Gemba connect with CFT - WPI Progress review | 849Q000009869
861YAA0024099 | bar: Day to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Station - 1 : Pilot Station ( C10 ) | P | bar: M to W
A | bar: M to F; M to F; M to F; M to F; M to F; M
Station - 2 : PBS | P | bar: T to S
A | bar: M to F
Station - 3 : T10RH | P | bar: M to W
A | bar: M to F; M to F
Station - 4 : T10LH | P | bar: T to S
A | bar: M to F
Station - 5 : T20RH | P | bar: M to W
A | bar: M to F; M to F
Station - 6 : T20LH | P | bar: T to S
A
Station - 7 : T20ENG | P | bar: M to W
A
Station - 8 : T30RH | P | bar: T to S
A
Station - 9 : T30LH | P | bar: M to W
A
Station - 10 : T30ENG | P | bar: T to S
A
Station - 11 : T40RH | P | bar: M to W
A
Station - 12 : T50RH | P | bar: T to S
A
Station - 13 : T50LH | P | bar: M to W
A
Station - 14 : T60ENG | P | bar: T to S
A
Station - 15 : T70RH | P | bar: M to W
A
Station - 16 : T70LH | P | bar: T to S; S
A
Station - 17 : T90RH | P | bar: M to W
A | bar: S
Station - 18 : T90LH | P | bar: T to S
A
Station - 19 : C40RH | P | bar: M to W; S
A
Station - 20 : P10LH | P | bar: T to S
A | bar: S
Station - 21 : P20LH | P | bar: M to W
A
Station - 22 : P30RH | P | bar: T to S; S
A
Station - 23 : P30LH | P | bar: M to W
A
Station - 24 : C45RR | P | bar: T to S
A
Station - 25 : R20 | P | bar: M to W
A
Station - 26 : C70 | P | bar: T to S
A
Station - 27 : C80RH | P | bar: M to W
A
Station - 28 : F10RH | P | bar: T to S
A
Station - 29 : F10LH | P | bar: M to W
A
Station - 30 : F10ENG | P | bar: T to S
A
Station - 31 : F20RH | P | bar: M to W
A
Station - 32 : F20LH | P | bar: T to S
A
Station - 33 : F30RH | P | bar: M to W
A
Station - 34 : F30LH | P | bar: T to S
A
Station - 35 : F40RH | P | bar: M to W
A
Station - 36 : F40LH | P | bar: T to S
A
Station - 37 : F60RH | P | bar: M to W
A
Station - 38 : F60LH | P | bar: T to S
A
Station - 39 : F70RH | P | bar: M to W
A
Station - 40 : F70LH | P | bar: T to S
A
Station - 41 : F80RH | P | bar: M to W
A
Station - 42 : F80LH | P | bar: T to S
A
Station - 43 : F90RH | P | bar: S to T
A
Station - 44 : F90LH | P | bar: W to F
A
Today
100% Station Assessment Completion -WK48
Current Status :
- 80% Pilot Station Assessment Completed.
- O&R / SQAM & JSRA Reassessment Planned
- 100% Completion by 7th Aug
WPI STATION ASSESSMENT COMPLETE OUT OF 05/15 CATCH UP THE UPCOMING WEEKS

## WPI Implementation Plan - OLD (hidden)
WPI Station Wise Assessment Timing Plan
| Year - 2026 | [156 empty] | Year - 2027
| 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | Sep'26 | [29 empty] | Oct'26 | [30 empty] | Nov'26 | [29 empty] | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
|  |  |  | WK27 |  |  |  |  | WK28 | [6 empty] | WK29 | [6 empty] | WK30 | [6 empty] | WK31 | [6 empty] | WK32 | [6 empty] | WK33 | [6 empty] | WK34 | [6 empty] | WK35 | [6 empty] | WK36 | [6 empty] | WK37 | [6 empty] | WK38 | [6 empty] | WK39 | [6 empty] | WK40 | [6 empty] | WK41 | [6 empty] | WK42 | [6 empty] | WK43 | [6 empty] | WK44 | [6 empty] | WK45 | [6 empty] | WK46 | [6 empty] | WK47 | [6 empty] | WK48 | [6 empty] | WK49
MEA | CM | SFM | [20 empty] | SHRM | [104 empty] | X1 | [28 empty] | 2026-12-01: X2; 2027-02-01: LRM / X3; 2027-03-01: PBM; 2027-04-01: BM/SOP
MEA | CM |  | SFM | [75 empty] | SHRM | [77 empty] | 2027-02-01: X1; 2027-03-01: X2; 2027-05-01: LRM/X3; 2027-06-01: PBM; 2027-07-01: BM/SOP
WPI LOOP | -2 | -1 |  | 0 | [81 empty] | 1 & 2 & 3 | [41 empty] | 4 | [28 empty] | 2027-03-01: 5
Activity Details |  |  | Date | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30
|  |  | Day | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Workstation Layout Readiness including Logistics flow |  |  | F: WPI Visit at RJN Pant; T: Workstation layout readiness & logistics flow assessment
JSRA risk assessment |  |  | W: Station wise Job Safety Risk Assessment
Papper Scroll Mapping |  |  | T: Station wise overall papper scroll mapping & actions convergence
O&R ( Lite PFMEA ) |  |  | T: Detailed station process wise O&R study with QCP
Proactive SQAM Assessment |  |  | F: Process wise SQAM assessment
Line Balancing Workshop ( VA & NVA assessment ) |  |  | T: Station wise Value Added & Non-Value added study & NVA Reduction opportunity identification
JES creation ( Digi JES with Conversion of Local language ) | [166 empty] | MZZCCHME8TV040854 9T | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Workstation Grid Validation | [166 empty] | 883QAB3023236 | bar: M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to T
Daily CFT Gemba Meeting ( 4:30 : 5:30 PM ) |  |  | M: *Daily Gemba connect with CFT - WPI Progress review | [10 empty] | 849Q000009869
861YAA0024099 | bar: Day to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F; M to F
Station - 1 : Pilot Station ( C10 ) |  |  | M: LL Validation; W: Station Layout Validation; W: JSRA / Ergo assessment; W: VA / NVA study; M: O&R and Logistics assessment
Station -2 | bar: M to T
Station -3 | bar: W to T
Station -4 | bar: F to S
Station -5 | bar: M to T
Station -6 | bar: W to T
Station -7 | bar: F to S
Station -8 | bar: M to T
Station -9 | bar: W to T
Station -10 | bar: F to S
Station -11 | bar: M to T
Station -12 | bar: W to T
Station -13 | bar: F to S
Station -14 | bar: M to T
Station -15 | bar: W to T
Station -16 | bar: F to S
Station -17 | bar: M to T
Station -18 | bar: W to T
Station -19 | bar: F to S
Station -20 | bar: M to T
Station -21 | bar: W to T
Station -22 | bar: F to S
Station -23 | bar: M to T
Station -24 | bar: W to T
Station -25 | bar: F to S
Station -26 | bar: M to T
Station -27 | bar: W to T
Station -28 | bar: F to S
Station -29 | bar: M to T
Station -30 | bar: W to T
Station -31 | bar: F to S
Station -32 | bar: M to T
Station -33 | bar: W to T
Station -34 | bar: F to S
Station -35 | bar: M to T
Station -36 | bar: W to T
Station -37 | bar: F to S
Station -38 | bar: M to T
Station -39 | bar: W to T
Station -40 | bar: F to S
Station -41 | bar: M to T
Station -42 | bar: W to T
Station -43 | bar: F to S
Station -44 | bar: M to T
Station -45 | bar: W to T
Today
100% Station Assessment Completion -WK48
Current Status :
- 80% Pilot Station Assessment Completed.
- O&R / SQAM & JSRA Reassessment Planned
- 100% Completion by 7th Aug
WPI STATION ASSESSMENT COMPLETE OUT OF 05/15 CATCH UP THE UPCOMING WEEKS